## Slide 1: 2020 Construction Logistics CSU Main Campus
Revision Update: 01/30/2020

## Slide 2
Construction Impacts – (Mid January – February 2020)
Lagoon
Nutrien Agricultural
Sciences Building
(Shepardson)
Meridian
Village Ph 1
Libbie Coy Way Closed through Summer 2021
Revision date: 02/10/2020
Note: construction dates are subject to change
South bike lane and Sidewalk Closed end of Feb.
Hughes Way

## Slide 3
Construction Impacts – (March – Mid May 2020)
Hughes Way
Lagoon
Amy Van Dyken/ Univ. Ave/ Lot 350 Closed
South bike lane and Sidewalk Closed
Libbie Coy Way Closed through Summer 2021
Meridian
Village Ph 1
Note: construction dates are subject to change
Nutrien Agricultural
Sciences Building
(Shepardson)
Revision date: 01/30/2020

## Slide 4
Construction Impacts – (Mid May – June 2020)
Hughes Way
Lagoon
Geo X
Ph1
LSC
LSC
Laydown
Amy Van Dyken/ Univ. Ave/ Lot 349 & 350 Closed
Street and parking closed
Libbie Coy Way Closed through Summer 2021
Lot
412
Temporary Access Road for Lot 425 Access
LSC Renovations through Summer 2021
Meridian
Village
Ph 1
Lot 425
Sanitary Line
Replacement
Meridian
Ave. Closed
Note: construction dates are subject to change
Nutrien Agricultural
Sciences Building
(Shepardson)
Revision date: 01/30/2020
Street and
Parking Closed
Industrial
Science Lab

## Slide 5
Construction Impacts – (June – July 2020)
Hughes Way
Lagoon
Geo X
Ph1
LSC
LSC
Laydown
Street and parking closed
Libbie Coy Way Closed through Summer 2021
Lot
412
Temporary Access Road for Lot 425 Access
LSC Renovations through Summer 2021
Meridian
Village
Ph 1
Lot 425
NCAA Women’s
Soccer & Softball
Complex
Sanitary Line
Replacement
Street Paving
Street Paving
Street Paving
Street Paving
Meridian
Ave. Closed
Amy Van Dyken/ Univ. Ave/ Lot 349 & 350 Closed
Note: construction dates are subject to change
Nutrien Agricultural
Sciences Building
(Shepardson)
Revision date: 01/30/2020
Street and
Parking Closed
Industrial
Science Lab

## Slide 6
Construction Impacts – (July – Mid August 2020)
Hughes Way
Univ. Ave Closed
Geo X
Ph1
LSC
LSC
Laydown
Street and parking closed
Temporary Access Road for Lot 425 Access
Lot 425
Libbie Coy Way Closed through Summer 2021
Lot
412
LSC Renovations through Summer 2021
Meridian
Village
Ph 1
Meridian
Ave. Closed
NCAA Women’s
Soccer & Softball
Complex
Sanitary Line
Replacement
Street Paving
Street Paving
Street Paving
Street Paving
Street Paving
Elevator
Replacement
Note: construction dates are subject to change
Nutrien Agricultural
Sciences Building
(Shepardson)
Revision date: 01/30/2020
Street and
Parking Closed
Industrial
Science Lab

## Slide 7
Construction Impacts - Mid August - Oct 2020
LSC
LSC
Laydown
Libbie Coy Way Closed through Summer 2021
Geo X
Ph2
Geo X
Ph1
LSC Renovations through Summer 2021
NCAA Women’s
Soccer & Softball
Complex
Meridian
Village
Ph 1
Note: construction dates are subject to change
Nutrien Agricultural
Sciences Building
(Shepardson)
Revision date: 01/30/2020

## Slide 8
Construction Impacts – (Oct. – Dec. 2020)
LSC
Laydown
Libbie Coy Way Closed through Summer 2021
Geo X
Ph2
NCAA Women’s
Soccer & Softball
Complex
LSC Renovations through Summer 2021
Meridian
Village
Ph 1
To be Completed Summer 2021
To be Completed Spring 2021
To be Completed Summer 2022
LSC
Note: construction dates are subject to change
Nutrien Agricultural
Sciences Building
(Shepardson)
Revision date: 01/30/2020

## Slide 9: South Campus:
Johnson Family Equine Hospital
Bay Facility
South Campus Utility Infrastructure
Foothills Campus:
CVID
Central Chill Plant
Temple Grandin Equine Center
Mountain Campus:
Wastewater Treatment Facility
Learning Center
* Along with Maintenance and Remodel Projects
Additional Campus Construction Projects
Revision date: 01/30/2020

## Slide 10: Communication and Outreach Plan:
Additional Presentations in 2020
Social Media
Source
Other News Media (Collegian, Coloradoan, etc.)
On-Site Project Posters
Display Information at Key Locations
Facilities Management Website
Tim Kemp, Asst. Director for Engineering and Capital Construction
Facilities Management
tim.kemp@colostate.edu
Office: 970.491.0051
Cell: 970.219.9762
Contact Information:
Revision date: 01/30/2020